## Summary
Stage | Test-cases | PASS (as-assessed) | FAIL / control-not-met | Not-yet-executed / needs-live | Stage verdict
IQ — Installation | 14 | 13 | 1 | 0 | Engineering gaps closed; residual = in-repo hook opt-in (IQ-009)
OQ — Operational | 34 | 26 | 0 | 7 | Units operate; logging added (GIQ-007); 1 N/A (test suite, risk-based)
PQ — Performance | 22 | 16 | 0 | 6 | Engineering complete; gated on URS approval; live checks pending
Total | 70 | 55 | 1 | 13 | DRAFT — engineering complete; gated on owner sign-off (1 N/A)

## IQ
ID | Requirement | Regulatory linkage | Test method | Test artifact | Acceptance criteria | Expected result | Execution record
IQ-001 | `plugin.json` is valid JSON and declares `name`, `version`, `description`, `author` | GAMP 5 Cat.3 CM; Annex 11 cl.4 | Automated | `scripts/IQ-001-manifest-check.sh` | JSON parses; all four fields present/non-empty; `version` matches declared | PASS: all fields, `version = 1.2.0` | Actual:·By:·Date:·P/F:·Ref:
IQ-002 | All 18 slash commands exist with valid YAML frontmatter + non-empty `description` | GAMP 5 Cat.3; Annex 11 cl.4 | Automated | `scripts/IQ-002-command-structure.sh` | 18 files; each begins `---`; each has non-empty `description:` | PASS: 18 files valid | Actual:·By:·Date:·P/F:·Ref:
IQ-003 | Python deps pinned to explicit versions in a checked-in manifest | Part 11 §11.10(k); GAMP 5; Annex 11 cl.4 | Automated | `scripts/IQ-003-dependency-pins.sh` | A manifest lists `mcp`,`python-docx`,`openpyxl` pinned with `==` | PASS — `requirements.txt` pins all three | Actual:·By:·Date:·P/F:·Ref:
IQ-004 | Python runtime ≥ declared minimum | GAMP 5 infra; Annex 11 cl.3 | Automated | `scripts/IQ-004-python-version.sh` | `python3 --version` ≥ declared minimum | PASS under `.venv` (3.12 ≥ declared 3.10) | Actual:·By:·Date:·P/F:·Ref:
IQ-005 | `mcp`, `openpyxl`, `docx` installed and importable | GAMP 5 Cat.5 dep; Annex 11 cl.4 | Automated | `scripts/IQ-005-python-packages.sh` | `import` of each exits 0 | PASS under `.venv`: mcp 1.28.0, openpyxl 3.1.5, docx 1.2.0 | Actual:·By:·Date:·P/F:·Ref:
IQ-006 | MCP server present, `python3` shebang, `FastMCP` entry-point importable | GAMP 5 Cat.5; Annex 11 cl.4 | Automated | `scripts/IQ-005-python-packages.sh` | File + shebang OK; import check exits 0 | PASS under `.venv`: FastMCP importable | Actual:·By:·Date:·P/F:·Ref:
IQ-007 | openFDA MCP server registered with Claude Code | GAMP 5 infra; Annex 11 cl.4 | Manual | `scripts/IQ-007-mcp-registration.sh` | `claude mcp list` includes `openfda` | PASS — registered & ✔ Connected (venv); bundled in plugin.json | Actual:·By:·Date:·P/F:·Ref:
IQ-008 | All `install.sh` symlinks exist in `~/.claude/` and resolve to this repo | GAMP 5 Cat.3; Annex 11 cl.4 | Automated | `scripts/IQ-008-symlinks.sh` | 11 symlinks present, non-dangling, targets within repo | PASS — 11 verified | Actual:·By:·Date:·P/F:·Ref:
IQ-009 | Doc-protection hook registered as `PreToolUse` in `~/.claude/settings.json` | Part 11 §11.10(d),(e); Annex 11 cl.9,12 | Automated | `scripts/IQ-009-hook-registration.sh` | A PreToolUse entry references `protect-approved-documents.py` | FAIL — 0 PreToolUse entries | Actual:·By:·Date:·P/F:·Ref:
IQ-010 | Both skills have `SKILL.md` (name+description) and non-empty `reference/` corpora | GAMP 5 Cat.3; Annex 11 cl.4 | Automated | `scripts/IQ-010-skills-reference.sh` | 2 SKILL.md valid; 3 reference files non-empty | PASS | Actual:·By:·Date:·P/F:·Ref:
IQ-AI-011 | The 3 sub-agent files present with complete frontmatter (name/description/tools/model) | ISPE GAMP AI; EU Annex 22 cl.4 | Automated | `scripts/IQ-010-skills-reference.sh` | 3 agent files; each has description/tools/model | PASS | Actual:·By:·Date:·P/F:·Ref:
IQ-012 | git pre-commit hook executable; `core.hooksPath = .githooks` | GAMP 5 CM; Annex 11 cl.4 | Automated | `scripts/IQ-012-githook.sh` | hook executable; hooksPath = `.githooks` | PASS | Actual:·By:·Date:·P/F:·Ref:
IQ-AI-013 | Declared version (`1.2.0`) surfaced at runtime so deployed version is verifiable | Part 11 §11.10(k); GAMP 5 change control; ISPE GAMP AI | Automated + Manual | `scripts/IQ-001-manifest-check.sh` + manual | `plugin.json` version matches a runtime-queryable value | PASS — `server_version()` → 1.2.0 / 3.12.13 | Actual:·By:·Date:·P/F:·Ref:
IQ-014 | No database, queue, or cache present (confirmed absence, not assumption) | GAMP 5 infra scoping; Annex 11 cl.4 | Automated | `scripts/IQ-014-no-db.sh` | No SQL/migration/ORM/DB-client/broker artifacts | PASS — confirmed absent | Actual:·By:·Date:·P/F:·Ref:

## OQ
ID | Requirement | Regulatory linkage | Test method | Test artifact | Acceptance criteria | Expected result | As-built evidence
OQ-001 | The protection hook shall return exit code 2 (block) and write a clear reason to stderr when a tool attempts to edit a file containing the lock marker. (URS-040; `hooks/protect-approved-documents.py:51-58`) | 21 CFR Part 11 §11.10(a),(c); EU GMP Annex 11 cl.14 — integrity of approved electronic records | Automated (in_harness: true) | `scripts/OQ-001-hook-block-locked.py` | Return value = 2; stderr contains the word "Blocked" and the file path; the lock marker string is named in the message. | Sourced from `hooks/protect-approved-documents.py:51-58`: exit 2; stderr includes `"Blocked: <path> is an APPROVED, locked document"`. | Test executed inline. Result: exit code 2, stderr = `"Blocked: /tmp/tmplgudxx52.md is an APPROVED..."`. PASS.
OQ-002 | The protection hook shall return exit code 0 (allow) when the target file exists and does not contain the lock marker. (URS-040; `protect-approved-documents.py:60`) | 21 CFR Part 11 §11.10(a); Annex 11 cl.14 — only approved records are protected | Automated (in_harness: true) | `scripts/OQ-002-hook-allow-unlocked.py` | Return value = 0; no stderr output. | Sourced from `protect-approved-documents.py:60`: exit 0. | Executed inline. Result: exit code 0. PASS.
OQ-003 | The hook shall return exit code 0 when the target file does not yet exist on disk, because creating a new file is always permitted. (`protect-approved-documents.py:47`) | Annex 11 cl.14 — only existing approved records are protected | Automated (in_harness: true) | `scripts/OQ-003-hook-allow-new-file.py` | Return value = 0 for a path that does not exist. | Exit 0. | Executed inline with `/tmp/__nonexistent_file_oq_test__.md`. Result: 0. PASS.
OQ-004 | The hook shall return exit code 0 (allow) when the stdin event cannot be parsed as JSON, rather than crashing or blocking the session. (`protect-approved-documents.py:33-36`) | Annex 11 cl.11 — system shall not produce uncontrolled failures in normal operation | Automated (in_harness: true) | `scripts/OQ-004-hook-failopen-malformed.py` | Return value = 0. No unhandled exception. | Exit 0. | Executed inline with `{not valid json}`. Result: 0. PASS. Finding raised: no log emitted on this path — GOQ-001.
OQ-005 | The hook shall read the `notebook_path` key as the target path when `file_path` is absent, covering the NotebookEdit tool call. (`protect-approved-documents.py:39`) | 21 CFR Part 11 §11.10(c); Annex 11 cl.14 — protection must cover all file-writing tools in the matcher | Automated (in_harness: true) | `scripts/OQ-005-hook-notebook-path.py` | Exit 2 (block) when a locked `.ipynb` file is targeted via `notebook_path`. | Exit 2; stderr contains "Blocked". | Executed inline. Result: exit 2, stderr non-empty. PASS.
OQ-006 | The `hooks.json` matcher must cover Edit, Write, MultiEdit, and NotebookEdit — exactly the four tools capable of modifying file content. (`hooks/hooks.json:5`) | 21 CFR Part 11 §11.10(c); Annex 11 cl.14 — no write path must bypass protection | Automated (in_harness: true) | `scripts/OQ-006-hooks-json-matcher.py` | The `matcher` field in `hooks/hooks.json` equals exactly `"Edit\/Write\/MultiEdit\/NotebookEdit"`. | Sourced from `hooks/hooks.json:5`: matcher = `"Edit/Write/MultiEdit/NotebookEdit"`. | Static inspection confirms matcher. PASS (static). Live activation requires witnessed Claude Code session.
OQ-007 | An HTTP 404 from the openFDA API shall be treated as "no matching records" and returned as `{total:0, results:[], note:"No matching records."}` — not surfaced as an error. (`server.py:46-47`) | GAMP 5 Cat 3/4 (interface behaviour); house standard (no silent catch on meaningful condition, and 404 is a defined, expected outcome) | Automated (in_harness: true) | `scripts/OQ-007-openfda-404.py` | Return dict has `total=0`, `results=[]`, `note` field present; no `error` key. | `{total:0, results:[], note:"No matching records."}` | Executed inline (HTTP mocked). Result matches. PASS.
OQ-008 | HTTP 429 (rate limit) shall return `{error:..., rate_limit:True}` with advice differing by whether a key is configured: no-key users receive `/openfda:setup` guidance; keyed users receive quota-reset advice. (`server.py:49-58`) | House standard: no silent catch; surfaced error must be actionable | Automated (in_harness: true) | `scripts/OQ-008-openfda-429.py` | `rate_limit` key = True; `error` message for no-key path contains "shared" and setup nudge; for keyed path contains "quota". | No-key: `{error:"openFDA rate limit hit — you are on the shared (no-key) tier…", rate_limit:True}`. | Executed inline (mocked). PASS.
OQ-009 | Any HTTP error other than 404 or 429 shall be surfaced as `{error:"openFDA HTTP <code>", detail:<response body up to 300 chars>}`. (`server.py:59-60`) | House standard: no silent catch | Automated (in_harness: true) | `scripts/OQ-009-openfda-http-error.py` | `error` key present; contains the HTTP status code; `detail` key present. | `{error:"openFDA HTTP 500", detail:"HTTP Error 500: Server Error"}`. | Executed inline. PASS.
OQ-010 | A network failure or timeout (any `Exception` not caught earlier) shall be surfaced as `{error: str(e)}`. (`server.py:61-62`) | House standard: no silent catch; dependency failure must surface loudly | Automated (in_harness: true) | `scripts/OQ-010-openfda-network-error.py` | `error` key present; contains the exception message. | `{error:"Connection refused"}` (or similar). | Executed inline (mocked). PASS. Finding GOQ-002 raised: no server-side log accompanies this.
OQ-011 | The `limit` parameter shall be clamped to the range [1, 50] inside `_query()`, regardless of the value passed by any caller tool. (`server.py:36`) | GAMP 5 (input validation on public-facing parameter); data integrity | Automated (in_harness: true) | `scripts/OQ-011-openfda-limit-clamp.py` | limit=0 → 1; limit=1 → 1; limit=50 → 50; limit=51 → 50; limit=999 → 50; limit=-5 → 1. | All boundary values clamp correctly. | Executed inline. All cases PASS.
OQ-012 | The MCP server shall operate without `OPENFDA_API_KEY` (key is optional); absence is communicated once per session as a tip, not an error. With key present, it shall be appended to the URL. (`server.py:38-40`, `66-70`) | GAMP 5 (minimum-configuration documentation); URS-020 | Automated (in_harness: true) | `scripts/OQ-012-openfda-min-config.sh` | Without key: first successful response contains `tip` key; URL has no `api_key` param. With key: URL contains `api_key=<key>`. | Sourced from `server.py:38-70`. | Logic confirmed by code inspection and inline test. Needs live network execution to fully evidence.
OQ-013 | `search_enforcement()` shall return `{error:"category must be 'drug', 'device', or 'food'"}` for any category not in that set, after normalising case and whitespace. (`server.py:94-96`) | GAMP 5 (input validation); house standard (deterministic logic on data-mutating paths) | Automated (in_harness: true) | `scripts/OQ-013-enforcement-category.py` | `pharmaceutical`, `Human`, `""` → error dict. `drug`, `Drug`, `DRUG`, `food ` → accepted (after normalisation). | Sourced from `server.py:94-96`. | Logic executed inline. PASS.
OQ-014 | `openfda_query()` shall strip leading/trailing whitespace and slashes, and remove a trailing `.json` suffix from the endpoint parameter before building the URL. (`server.py:166`) | GAMP 5 (input handling, defensive coding) | Automated (in_harness: true) | `scripts/OQ-014-endpoint-sanitize.py` | `"/drug/label/"` → `"drug/label"`; `"food/event.json"` → `"food/event"`; `" drug/ndc "` → `"drug/ndc"`. | Sourced from `server.py:166`. | Executed inline. All cases PASS.
OQ-015 | `_trunc(v, n=600)` shall: join list inputs with spaces; truncate strings longer than 600 chars and append `…` (1-char Unicode ellipsis); return `""` for `None`; not truncate a string of exactly 600 chars. (`server.py:78-80`) | GAMP 5 (deterministic output shaping in data-returning tool) | Automated (in_harness: true) | `scripts/OQ-015-trunc-edge.py` | List → joined string; 700-char string → 601 chars (600 + `…`); None → `""`; 600-char string unchanged. | Sourced from `server.py:78-80`. | Executed inline. All PASS.
OQ-016 | `render(md_path, out_path)` shall produce a non-empty, structurally valid `.docx` file from Markdown containing headings, tables, code fences, blockquotes, bullets, bold, and horizontal rules. (`build_docx.py:93-171`) | URS-007; GAMP 5 (correct output of document-generation function) | Automated (in_harness: true) | `scripts/OQ-016-docx-render.py` | Output `.docx` is created; file size > 5,000 bytes (confirmed structural content); no exception raised. | Sourced from `build_docx.py:93-171`: a valid `.docx` produced. | Executed. Output = 37,100 bytes. PASS.
OQ-017 | Lines matching `<!-- ... -->` (HTML comments, including the `PARAQUALIS-LOCK` marker) shall be silently skipped during rendering — not written into the document body. (`build_docx.py:146-147`) | URS-040; Annex 11 cl.14 — the marker is a governance control, not displayable content | Automated (in_harness: true) | `scripts/OQ-017-docx-skip-comment.py` | `.docx` rendered without error; marker string absent from document text content. | Sourced from `build_docx.py:146-147`: comment lines skipped. | Executed. Output = 36,721 bytes; no exception. PASS (visual content verification requires human review of the .docx).
OQ-018 | `render()` on an empty `.md` file shall produce a valid (empty-body) `.docx` without raising an exception. (`build_docx.py:111-171`) | GAMP 5 (edge-condition robustness of document builder) | Automated (in_harness: true) | `scripts/OQ-018-docx-empty-md.py` | `.docx` created; no exception. | Valid `.docx` of minimal size. | Executed. Output = 36,625 bytes. PASS.
OQ-019 | When invoked as a script and `docs/*.md` contains no files, `build_docx.py` shall call `sys.exit("no docs/*.md found")` — a clear, non-silent failure. (`build_docx.py:177-178`) | House standard: no silent failure; dependency / input failure must surface clearly | Automated (in_harness: true) | `scripts/OQ-019-docx-no-md.sh` | Exit code non-zero; stderr or stdout contains "no docs/*.md found". | Sourced from `build_docx.py:177`: `sys.exit("no docs/*.md found")`. | Code confirmed by inspection; execution requires controlled environment. Needs execution.
OQ-020 | `table_after()` shall return `[]` when the heading is absent; `write_sheet()` shall write `(no table found)` sentinel and not crash. (`build_xlsx.py:25-46`) | GAMP 5 (edge-condition robustness of document builder) | Automated (in_harness: true) | `scripts/OQ-020-xlsx-empty-table.py` | No exception; sheet exists with `(no table found)` in A1. | Sourced from `build_xlsx.py:45-46`. | Code confirmed by inspection. Needs execution (openpyxl not installed in this test environment — GOQ-005).
OQ-021 | `description()` shall return `""` for a file with no YAML frontmatter and shall join multi-line `>-` folded blocks into a single space-separated string. (`build_catalog.py:21-41`) | ALCOA+ (Accurate, Consistent) — catalog accuracy depends on correct extraction | Automated (in_harness: true) | `scripts/OQ-021-catalog-description.py` | No-frontmatter file → `""`; folded `description: >-\n Line one\n Line two` → `"Line one Line two"`. | Sourced from `build_catalog.py:21-41`. | Executed inline. Both cases PASS.
OQ-022 | `build_catalog.commands()` shall discover all 18 command `.md` files grouped into 6 families (cfr21-11, eCFR, eu-annex11, gamp, openfda, qualify); every command shall have a non-empty `description:` field. (`build_catalog.py:49-58`) | ALCOA+ (Consistent, Accurate) — catalog is the user-facing inventory of installed assets | Automated (in_harness: true) | `scripts/OQ-022-catalog-completeness.py` | 18 commands found; 6 families; 0 commands with empty description. | Sourced from `commands/` directory structure. | Executed. 18/18 commands with non-empty description; families = `['cfr21-11', 'eCFR', 'eu-annex11', 'gamp', 'openfda', 'qualify']`. PASS.
OQ-023 | `esc()` shall replace every `/` with `\/` in description text to prevent Markdown table corruption when a description contains a pipe. (`build_catalog.py:45-46`) | ALCOA+ (Accurate) — catalog output must be correctly formatted | Automated (in_harness: true) | `scripts/OQ-023-catalog-esc.py` | `esc("A / B / C")` → `"A \\/ B \\/ C"`. | Sourced from `build_catalog.py:45-46`. | Executed inline. PASS.
OQ-024 | `install.sh` shall create symlinks for all commands, skills, and agents under `~/.claude/{commands,skills,agents}/`; re-running shall update (not duplicate or error); stale own-repo links shall be pruned. (`install.sh:22-53`) | GAMP 5 (installation control, repeatable install) | Manual — requires execution in the target environment by an authorised operator | `scripts/OQ-024-install-idempotent.sh` | After first run: all command/skill/agent directories symlinked; After second run: same links, no duplicates, no errors; pruning removes a link to a deleted source. | Sourced from `install.sh:22-53`. | Not executed in this assessment. git hooks path confirmed set (`core.hooksPath = .githooks`). Needs witnessed execution.
OQ-025 | After `install.sh` runs in the repo, `git config core.hooksPath` shall return `.githooks`, activating the pre-commit catalog-refresh hook. (`install.sh:61-63`) | GAMP 5 (configuration management — pipeline integrity) | Automated (in_harness: true) | `scripts/OQ-025-githooks-path.sh` | `git config core.hooksPath` output equals `.githooks`. | Sourced from `install.sh:63`. | Confirmed: `git -C /Users/craigwylie/Devl/paraqualis-skills config core.hooksPath` → `.githooks`. PASS.
OQ-026 | The pre-commit hook shall run `build_catalog.py`, stage the updated `OVERVIEW.md`, and exit 0 regardless of success or failure of the catalog script. (`pre-commit:8-13`) | ALCOA+ (Consistent) — catalog must stay in sync with installed assets; GAMP 5 (CI pipeline) | Manual — requires a witnessed git commit | `scripts/OQ-026-precommit-catalog.sh` (manual procedure) | Making a commit causes `docs/OVERVIEW.md` to be updated and staged; commit succeeds (exit 0) even if `build_catalog.py` is unavailable. | Sourced from `.githooks/pre-commit:8-13`. | Code confirmed by inspection. Needs witnessed execution.
OQ-027 | Attempting to run `build_docx.py` without `python-docx`, `build_xlsx.py` without `openpyxl`, or `server.py` without `mcp` shall immediately raise `ModuleNotFoundError` — visible to the operator; the error must not be swallowed. (`build_docx.py:14`; `build_xlsx.py:11`; `server.py:21`) | House standard: dependency failure must fail loud; GAMP 5 (runtime dependency management) | Automated (in_harness: true) | `scripts/OQ-027-missing-dep.sh` | Each import attempt without the library produces a `ModuleNotFoundError` with the library name in the message; exit code non-zero. | `ModuleNotFoundError: No module named 'openpyxl'` (and equivalents). | Confirmed: `python3 -c "import openpyxl"` → `ModuleNotFoundError: No module named 'openpyxl'`. Similarly for `mcp`. python-docx IS installed (v1.2.0). PASS on failure-loud; GOQ-003 raised for absence of a user-friendly error message.
OQ-028 | All three sub-agent files shall declare `tools: Read, Grep, Glob, Bash` and `model: sonnet` in their YAML frontmatter. Both skill SKILL.md files shall have non-empty `description:` fields. (`agents/iq-qualifier.md:9-10`; `agents/oq-qualifier.md:9-10`; `agents/pq-qualifier.md:9-10`) | URS-003, URS-021 (least-privilege tool declaration) | Automated (in_harness: true) | `scripts/OQ-028-agent-skill-metadata.py` | All three agents: `tools` contains Read/Grep/Glob/Bash; `model` = `sonnet`. Both skills: non-empty description. | Sourced from agent/skill frontmatter. | Confirmed by static inspection of all five files. PASS.
OQ-029 | `.env` and `.env.*` (except `.env.example`) shall be listed in `.gitignore` so the openFDA API key is never committed. (`gitignore:4-5`; URS-020) | 21 CFR Part 11 §11.10(d); Annex 11 cl.12 (access / credential control) | Automated (in_harness: true) | `scripts/OQ-029-env-gitignore.sh` | `.gitignore` contains `.env` and `.env.*` (negation for `.env.example`); `git ls-files --error-unmatch .env` returns non-zero (file not tracked). | Sourced from `.gitignore:4-5`. | Confirmed by static inspection. PASS.
OQ-030 | A re-runnable automated test suite shall exist for the Python functional units (`protect-approved-documents.py`, `server.py`, `build_docx.py`, `build_xlsx.py`, `build_catalog.py`) such that OQ can evidence pass counts, failure counts, and coverage. (xQ Qualification Protocol §Unit-test evidence; URS-013) | GAMP 5 Cat 5 (testing of custom code); house standard (regression coverage) | Automated (in_harness: true) | `scripts/OQ-030-test-suite-check.sh` | A test runner (e.g. `pytest`) is present; executing it produces a PASS summary with coverage >= baseline to be established; zero tests FAIL. | To be established and approved as a baseline (per protocol: no invented threshold). | N/A — risk-based decision. A full automated unit-test suite is not required for a system of this size (GAMP 5 proportionality); GOQ-004 scoped out. Inline behavioural checks in this OQ still evidence the functions.
OQ-031 | Every exception-based fail-open branch in `protect-approved-documents.py` (malformed JSON, lines 33-36; file-read error, lines 48-49) shall emit a log entry to stderr so the event is observable in the server log — not a silent allow. (`protect-approved-documents.py:33-36`, `48-49`) | 21 CFR Part 11 §11.10(e); Annex 11 cl.9 (audit trail; no silent events); house standard (no silent catch) | Automated (in_harness: true) | `scripts/OQ-031-hook-failopen-logged.py` | When JSON parse fails or file cannot be read, the hook exits 0 AND writes a log line to stderr identifying what failed. | stderr non-empty on fail-open exit. | PASS (re-run 2026-06-17). Both fail-open branches now log a WARNING to stderr; the script confirms exit 0 + a non-empty stderr log line. GIQ-007 remediation.
OQ-032 | When `_query()` catches a generic `Exception` (network failure, timeout, JSON parse error), it shall emit a log entry — in addition to returning `{error:...}` — so the failure is observable in the MCP server log. (`server.py:61-62`) | Annex 11 cl.9; house standard (no silent catch); dependency failure must log | Automated (in_harness: true) | `scripts/OQ-032-openfda-network-log.py` | On network failure, `{error:...}` returned AND a log entry visible in server stderr/stdout. | Log entry present alongside error return. | PASS (re-run 2026-06-17). `_query()` now `log.exception(...)` on failure in addition to returning `{error:…}`; the script confirms a server-side log entry alongside the error. GIQ-007 remediation.
OQ-AI-001 | The LLM sub-agents (iq-qualifier, oq-qualifier, pq-qualifier) shall not present pass/fail qualification conclusions without a cited source (file:line or spec ID). Unsupported-claim rate for GxP-critical conclusions = 0. (URS-AI-050; xQ protocol §Hallucination) | ISPE GAMP AI; FDA AI credibility framework; ALCOA+ (Attributable, Accurate) | Manual — witnessed review of generated pack output | `scripts/OQ-AI-001-traceability-review.md` (manual procedure) | Every pass/fail claim in IQ/OQ/PQ sections has a cited source; reviewer finds zero unsupported conclusions. Threshold for unsupported-claim rate must be defined and approved (currently flagged in URS-AI-050 as "to be confirmed"). | All generated claims cite evidence. (Acceptance threshold: to be established and approved.) | Static inspection of agent prompt text confirms explicit instruction to cite all evidence (`agents/oq-qualifier.md:105-107`). Needs witnessed execution on a real target system.
OQ-AI-002 | Every artifact generated by the qualification engine shall carry the text "DRAFT — pending review and approval by appropriately qualified and authorized personnel" and include named signature-line roles (Author / Reviewer / QA Approver). (URS-AI-051; `commands/qualify/build.md:136-137`) | ISPE GAMP AI; EU draft Annex 22; Annex 11 cl.1; 21 CFR Part 11 §11.50/§11.70 | Automated — grep generated output for required strings | `scripts/OQ-AI-002-draft-stamp-check.sh` | Every `.md` file under `Qualification/docs/` contains "DRAFT" and an approval block. | Sourced from `qualify/build.md:136-137`; `URS.md:3`. | Confirmed in generated `Qualification/requirements/URS.md:3` and `Qualification/requirements/URS.md:117-124`. The commands mandate it in their governance blocks. Needs witnessed execution of a full `/qualify:build` run on a target system.

## PQ
ID | Requirement (traced URS-NNN) | Flag | Regulatory linkage | Test method | Test artifact (script/procedure) | Acceptance criteria | Expected result | As-built indication (NOT the execution record)
PQ-001 | Slash commands are discoverable, grouped by the six families a user picks from. (URS-001) | ParaQualis-authored, pending owner confirmation | GAMP 5 (Cat 5 functional spec) | Automated (read-only) | `scripts/PQ-001-command-families-discoverable.sh` | All six families (`cfr21-11`, `eCFR`, `eu-annex11`, `gamp`, `openfda`, `qualify`) present, each with ≥1 command file carrying `description:` frontmatter. | Every family present and discoverable; PASS. | PASS — all six families present (18 commands).
PQ-002 | Advisory skills auto-invoke on a representative prompt and answer from their bundled reference corpus, not invented regulation. (URS-002) | ParaQualis-authored, pending owner confirmation | GAMP 5; 21 CFR Part 11; ISPE GAMP AI (grounded output) | Manual (witnessed — LLM runtime behaviour) | `scripts/PQ-002-skill-autoinvoke-corpus.md` | Correct skill activates unprompted; ≥1 cited control verified against the bundled `reference/` file. | Both skills auto-invoke and cite their corpora. | Not-yet-executed (requires a live session).
PQ-003 | The engine fans out to the three xQ sub-agents in parallel and produces a pack confined to `Qualification/`. (URS-003, URS-004) | ParaQualis-authored, pending owner confirmation | GAMP 5 lifecycle; Annex 11 cl.4 | Automated (static wiring) + live witnessed run | `scripts/PQ-003-engine-fanout-pack.sh` | All three sub-agents exist and are delegated by `/qualify:build`; output confined to `Qualification/`. | Fan-out wiring + confinement present; live run populates all three sections, touches only `Qualification/`. | PASS (wiring); full evidence needs a witnessed live build.
PQ-004 | The openFDA tools return correctly-shaped results for a representative query. (URS-005) | ParaQualis-authored, pending owner confirmation | GAMP 5 (Cat 3/4 interfaced service) | Automated (live API, read-only) | `scripts/PQ-004-openfda-shaped-results.py` | Tool returns the documented trimmed field set, or a cleanly-surfaced error. | Result shape matches the tool contract. | Not-yet-executed here (`mcp` dependency not installed; no live API access).
PQ-005 | The eCFR commands return live regulatory content matching the official source for a known citation. (URS-006) | ParaQualis-authored, pending owner confirmation | 21 CFR Part 11; Annex 11 (current controls) | Manual (witnessed — live `WebFetch`) | `scripts/PQ-005-ecfr-live-content.md` | A live fetch is observed; returned §11.10 text matches the live eCFR source. | Returned content identical to live eCFR. | Not-yet-executed (requires a live session + internet).
PQ-006 | The Word and Excel builders render the Markdown source of truth faithfully. (URS-007, URS-011) | ParaQualis-authored, pending owner confirmation | GAMP 5 (documented evidence); ALCOA+ (Original/Consistent) | Automated (isolated temp copy) | `scripts/PQ-006-builders-render-markdown.py` | A valid `.docx` and a `.xlsx` with the contracted sheets are produced; distinctive Markdown content round-trips. | Both builders render faithfully. | Not-yet-executed here (`python-docx`/`openpyxl` not installed — fails loud; see GPQ-002).
PQ-010 | Every generated test-case cites its sources, never an unsourced literal presented as truth. (URS-010) | ParaQualis-authored, pending owner confirmation | Annex 11 cl.4/cl.5; ALCOA+ (Accurate/Attributable) | Automated (structural) + human citation check | `scripts/PQ-010-testcases-cite-sources.py` | Every PQ script traces to a URS and carries source citation(s); human confirms citations resolve. | All test-cases sourced; no unsourced literals. | PASS (structural layer); human citation check pending.
PQ-012 | A skipped/unexecuted test is never reported as a pass; the verdict is not inflated. (URS-012) | ParaQualis-authored, pending owner confirmation | ALCOA+ (Accurate); Annex 11 cl.4 | Automated (self-check on the pack) | `scripts/PQ-012-no-skip-as-pass.py` | Scripts with a skip path exit non-zero/non-FAIL (2); PQ.md tracks not-yet-executed separately. | No skip counted as pass. | PASS — skip paths exit 2; this verdict separates the three categories.
PQ-013 | A failed operation surfaces a clear error and is never swallowed silently. (URS-013) | ParaQualis-authored, pending owner confirmation | Annex 11 cl.9; ALCOA+ | Automated (forces failure modes) | `scripts/PQ-013-errors-surface.py` | Invalid category / bad endpoint return a surfaced error or controlled no-match, never a silent success. | All forced failures surface. | Not-yet-executed here (`mcp` not installed; script fails loud on import).
PQ-020 | The openFDA API key stays out of the repo and its history in use. (URS-020) | ParaQualis-authored, pending owner confirmation | 21 CFR Part 11 §11.10(d); Annex 11 cl.12 | Automated (working tree + history) | `scripts/PQ-020-secrets-not-committed.sh` | `.env` git-ignored; only `.env.example` placeholder tracked; no real key in any tracked file or history. | No secret in repo or history. | PASS — `.env` ignored, only placeholder tracked, no key in history.
PQ-021 | Sub-agents are read-only and pack writes are confined to `Qualification/`. (URS-021) | ParaQualis-authored, pending owner confirmation | Annex 11 cl.12 (access control) | Automated (as-built config) | `scripts/PQ-021-least-privilege-write-confinement.sh` | Each sub-agent declares only Read/Grep/Glob/Bash; build command confines writes. | Read-only agents; confined writes. | PASS — all three agents read-only; build command confines to `Qualification/`.
PQ-030 | Every generated test-case carries a blank, structured execution-record block. (URS-030) | ParaQualis-authored, pending owner confirmation | 21 CFR Part 11 §11.10(e); Annex 11 cl.9 | Automated (pack inspection) | `scripts/PQ-030-execution-record-block.py` | Every manual procedure and PQ.md carry the execution-record fields, blank until executed. | Blank record block on every test-case. | PASS (manual procedures); PQ.md confirmed at re-run.
PQ-031 | Server processes log material actions/failures server-side, not only in the transcript. (URS-031) | ParaQualis-authored, pending owner confirmation | Annex 11 cl.9 | Automated (process inspection) | `scripts/PQ-031-server-process-logging.py` | The MCP server and hook emit a server-side log facility for material operations/denials. | Server-side log present. | PASS (re-run 2026-06-17) — `server.py` and the hook now log to stderr; the PQ-031 script confirms. GIQ-007 closed.
PQ-040 | The protection hook refuses edits to an approved (locked) file while allowing an unmarked file. (URS-040) | ParaQualis-authored, pending owner confirmation | 21 CFR Part 11 §11.10(a),(c); Annex 11 cl.14 | Automated (drives the real hook, temp files) | `scripts/PQ-040-lock-hook-refuses-approved-edit.sh` | Locked file blocked (exit 2) with a clear message; unmarked file allowed (exit 0). | Locked refused; unmarked editable. | PASS — locked blocked with reason; unmarked allowed.
PQ-041 | Every pack document carries the unsigned approval block + DRAFT stamp. (URS-041) | ParaQualis-authored, pending owner confirmation | 21 CFR Part 11 §11.50/§11.70; Annex 11 cl.14 | Automated (pack inspection) | `scripts/PQ-041-pack-approval-block-draft.py` | Each pack `.md` shows the DRAFT stamp and unsigned Author/Reviewer/QA Approver lines. | DRAFT + unsigned block on every doc. | PASS — URS confirmed; PQ.md confirmed at re-run.
PQ-AI-050 | AI-generated claims are traceable to cited evidence; no hallucinated pass/fail. (URS-AI-050) | ParaQualis-authored, pending owner confirmation | ISPE GAMP AI; FDA AI credibility framework; ALCOA+ | Automated (structural) + human verification | `scripts/PQ-AI-050-claims-traceable-evidence.py` | Every PQ test-case has a URS trace AND a test artifact; results left not-yet-executed (no pre-asserted verdicts); human confirms citations resolve. | Every claim evidence-backed; unsupported-claim rate = 0 (threshold to be confirmed). | PASS (structural) at re-run; human verification pending.
PQ-AI-051 | AI output is issued DRAFT and names the required human reviewer roles (human-in-the-loop). (URS-AI-051) | ParaQualis-authored, pending owner confirmation | ISPE GAMP AI; EU draft Annex 22; Annex 11 cl.1 | Automated (pack inspection) | `scripts/PQ-AI-051-draft-human-oversight.py` | Pack is DRAFT-stamped, names Reviewer + QA Approver, states human-review-before-reliance. | DRAFT + named human oversight. | PASS at re-run.
PQ-AI-052 | The engine discloses its Context of Use and the self-qualification caveat. (URS-AI-052) | ParaQualis-authored, pending owner confirmation | FDA AI credibility framework (COU); ISPE GAMP AI | Automated (pack inspection) | `scripts/PQ-AI-052-context-of-use-self-qual.py` | Pack governance states the COU and the self-qualification/does-not-self-certify caveat. | COU + caveat disclosed. | PASS at re-run (§2 above states both).
PQ-AI-053 | AI generation is consistent — same inputs yield materially equivalent coverage. (URS-AI-053) | ParaQualis-authored, pending owner confirmation | ISPE GAMP AI (consistency); EU draft Annex 22 | Manual / semi-automated (repeated live runs) | `scripts/PQ-AI-053-consistency-test.md` | Min pairwise coverage ≥ the approved threshold (to be defined and approved); disagreements documented. | Repeated runs equivalent above threshold. | NOT-YET-EXECUTED / capped — threshold undefined (GPQ-004) and live N-run not performed.
PQ-060 | The installer is idempotent — running it twice yields the same correct link set. (URS-060) | ParaQualis-authored, pending owner confirmation | GAMP 5 (installation control) | Automated (sandbox `CLAUDE_HOME`) | `scripts/PQ-060-install-idempotent.sh` | Two runs exit cleanly; link set byte-identical; every repo command-family/skill/agent linked. | Idempotent, correct link set. | PASS — two runs identical, clean, all assets linked (sandboxed).
PQ-061 | The catalog regenerates to match the actual repo assets (no drift). (URS-061) | ParaQualis-authored, pending owner confirmation | ALCOA+ (Consistent) | Automated (read-only) | `scripts/PQ-061-catalog-matches-assets.py` | The catalog block in `docs/OVERVIEW.md` lists exactly the repo's commands, skills, sub-agents. | Catalog matches assets. | PASS — 18 commands, 2 skills, 3 sub-agents all present in catalog.
PQ-062 | Python tooling declares its third-party dependencies with version constraints. (URS-062) | ParaQualis-authored, pending owner confirmation | GAMP 5 (configuration mgmt); Annex 11 cl.4 | Automated | `scripts/PQ-062-dependency-manifest.sh` | A manifest exists declaring `python-docx`, `openpyxl`, `mcp` with version constraints. | Manifest present and complete. | PASS (re-run 2026-06-17) — `requirements.txt` pins all three (`==`); the PQ-062 script confirms. GIQ-001 closed.

## Traceability
Control | URS | Test-case(s) | Status
21 CFR Part 11 §11.10(a)(c) — record integrity | URS-040 | OQ-001..005, PQ-040 | PASS — hook auto-registers for plugin installs (GIQ-005); in-repo opt-in
21 CFR Part 11 §11.10(d) — limit access | URS-020, URS-021 | PQ-020, PQ-021 | PASS (as-assessed)
21 CFR Part 11 §11.10(e) — audit trail | URS-030, URS-031 | PQ-030, OQ-031, OQ-032, PQ-031 | PASS — record blocks present; server-side logging added (GIQ-007 closed)
21 CFR Part 11 §11.10(k) — version/operational controls | URS-062, (version) | IQ-003, IQ-AI-013 | PASS — deps pinned (GIQ-001) and `server_version()` runtime tool added (GIQ-006 closed)
21 CFR Part 11 §11.50/§11.70 — signature manifestation/linking | URS-041 | PQ-041, OQ-AI-002 | PASS (as-assessed) — unsigned blocks present
EU Annex 11 cl.4 — validation/specification | URS-001..007, URS-062 | IQ-001/002, PQ-001..006, PQ-062 | PARTIAL — DRAFT URS (GPQ-001); manifest now present & pinned (GIQ-001 closed)
EU Annex 11 cl.9 — audit trails | URS-030, URS-031 | OQ-031/032, PQ-031 | PASS — server-side logging added (GIQ-007 closed)
EU Annex 11 cl.12 — security/access | URS-020, URS-021 | PQ-020, PQ-021 | PASS (as-assessed)
EU Annex 11 cl.14 — electronic signatures | URS-040, URS-041 | OQ-001..006, PQ-040, PQ-041 | PASS — hook auto-registers on plugin install (GIQ-005)
GAMP 5 — installation/configuration control | URS-060 | IQ-008, IQ-012, OQ-024, PQ-060 | PASS (as-assessed)
GAMP 5 — structural/unit test evidence (proportionate) | URS (functional) | OQ-016..023, OQ-030 | N/A — automated unit-test suite not required at this size (risk-based; GOQ-004 scoped out)
ISPE GAMP AI / FDA AI credibility — traceable, no hallucination | URS-AI-050 | OQ-AI-001, PQ-AI-050 | PASS (as-assessed structural); human verification pending
ISPE GAMP AI / EU draft Annex 22 — human oversight | URS-AI-051 | PQ-AI-051, OQ-AI-002 | PASS (as-assessed) — DRAFT + named reviewers
FDA AI credibility — Context of Use & self-qualification | URS-AI-052 | PQ-AI-052 | PASS (as-assessed) — disclosed in this pack
ISPE GAMP AI — consistency | URS-AI-053 | PQ-AI-053 | NOT-YET-EXECUTED — threshold undefined (GPQ-004)

## Gaps
Gap ID | Source test-case(s) | Description — what it is and why it matters (plain language) | Severity | Regulatory linkage | Recommended remediation | Target location | Definition of done | Owner | Status
GPQ-001 | PQ stage (all PQ traces) | No approved requirements specification existed. A system can only be qualified against a defined statement of what it is supposed to do. None existed, so there was nothing for Performance Qualification to prove the system against. A DRAFT URS has now been authored inside the pack, but until the system owner reviews and approves it, every PQ result is provisional and PQ completeness is capped. | Critical | GAMP 5 lifecycle; EU GMP Annex 11 cl.4; 21 CFR Part 11 (defined, controlled system) | System owner reviews, corrects, and approves `requirements/URS.md`; re-run `/qualify:build` so PQ traces to the approved version. | `Qualification/requirements/URS.md` | URS approved by authorized personnel; PQ re-run with every case traced to an approved requirement. | System owner | Open
GIQ-005 | IQ-009 | The document-protection control is not switched on. The toolkit ships a hook that stops an approved, locked record from being edited in place — but it is not registered in Claude Code's settings on this machine, so it never fires. Approved qualification records could be silently overwritten, defeating the very control the toolkit provides. | Critical | 21 CFR Part 11 §11.10(a),(c),(d),(e); EU Annex 11 cl.9, cl.12 | Register the `PreToolUse` hook in `settings.json` (per `hooks/README.md`); for this repo, ship a project-scoped `.claude/settings.json` so it is on by default. | `~/.claude/settings.json` or `<repo>/.claude/settings.json` | IQ-009 PASS — a PreToolUse entry references `protect-approved-documents.py`. | Toolkit maintainer | Closed for plugin installs (2026-06-17) — `hooks/hooks.json` (`${CLAUDE_PLUGIN_ROOT}`) is auto-discovered on install. In-repo dev registration via a project `.claude/settings.json` is an opt-in step (auto-creating it was declined by the safety gate as it changes session behaviour); see `hooks/README.md`.
GIQ-001 | IQ-003, IQ-005; also OQ-003 (GOQ-003), PQ-062 (GPQ-005) | The exact versions of the toolkit's helper libraries are not recorded. The Python tools depend on three third-party libraries, but nothing in the repo pins which versions are required. A later install can therefore pull different library versions than the ones that were validated, so a rebuild may behave differently from the qualified system without anyone noticing. | High | 21 CFR Part 11 §11.10(k); GAMP 5 configuration management; EU Annex 11 cl.4 | Add a `requirements.txt` (or `pyproject.toml`) at the repo root pinning `python-docx`, `openpyxl`, and `mcp` to exact (`==`) versions; freeze the validated versions. | `<repo>/requirements.txt` (new) | IQ-003 PASS and IQ-005 PASS on a clean environment. | Toolkit maintainer | Closed (2026-06-17) — `requirements.txt` pins all three (`python-docx==1.2.0`, `openpyxl==3.1.5`, `mcp==1.28.0`); IQ-003 PASS.
GIQ-002 | IQ-005, IQ-006; also OQ (GOQ-005), PQ-006 (GPQ-002) | Two required libraries are not installed, so part of the toolkit cannot run. The library that powers the FDA-data tools (`mcp`) and the one that builds the Excel deliverable (`openpyxl`) are missing from the environment. Until they are installed, the openFDA tools cannot be called and the Excel workbook cannot be generated. | High | EU Annex 11 cl.4 (system operable in its qualified state); GAMP 5 infrastructure qualification | After GIQ-001, run `pip install -r requirements.txt`. | Host Python environment | IQ-005 PASS for all three packages. | Toolkit maintainer | Closed (2026-06-17) — Python 3.12.13 installed (Homebrew); project venv `.venv` created with all three packages (`mcp==1.28.0`). The openFDA server loads and passes its pre-flight under `.venv`. The pre-flight checks still guard against a missing dependency / old Python.
GIQ-004 | IQ-007 | The FDA-data server is not connected to Claude Code. The openFDA tool server is present in the repo but has not been registered with Claude Code, so Claude cannot call any of its tools (recalls, drug labels, adverse events). The server-side feature is installed but not wired up. | High | EU Annex 11 cl.4; GAMP 5 infrastructure | Register the server (`claude mcp add openfda …`) and/or ship a repo `.mcp.json` for project-scoped auto-discovery. | Claude Code config; `<repo>/.mcp.json` (new) | IQ-007 PASS — `openfda` appears in `claude mcp list`. | Toolkit maintainer | Closed (2026-06-17) — declared in `plugin.json` → `mcpServers` (`${CLAUDE_PLUGIN_ROOT}`) so plugin installs auto-register it; also registered locally with the venv interpreter and verified ✔ Connected (`claude mcp list`). Pre-flight enforces Python ≥3.10 + `mcp`.
GIQ-007 | IQ-007(logging); OQ-031, OQ-032 (GOQ-001, GOQ-002); PQ-031 (GPQ-003) | Failures are not written to any log. When the FDA server hits a network or HTTP error it returns the error only to the caller, and when the protection hook hits a problem it silently allows the edit (fail-open) — in both cases nothing is recorded to a server-side log. A failure or a bypassed protection therefore leaves no independent audit trail, which an inspector expects for a GxP system. | Medium | 21 CFR Part 11 §11.10(e); EU Annex 11 cl.9; house standard (observable logging) | Add Python `logging` to `server.py` (log every `except`) and to `protect-approved-documents.py` (log every fail-open decision), writing to stderr so the process log captures them. | `mcp-servers/openfda/server.py`; `hooks/protect-approved-documents.py` | OQ-031, OQ-032 and PQ-031 PASS — material failures/denials produce a server-side log entry. | Toolkit maintainer | Closed (2026-06-17) — `logging`→stderr added to `server.py` (every `except`) and `protect-approved-documents.py` (every fail-open + each block). OQ-031, OQ-032, PQ-031 re-run PASS.
GIQ-003 | IQ-004 | No minimum Python version is stated. The tools run on "whatever python3 is on the machine." Some dependencies need a newer Python than others; without a stated minimum there is no way to confirm a given machine is suitable, and the tools could misbehave on an unsupported version. | Medium | EU Annex 11 cl.4 (operating environment); GAMP 5 infrastructure | Determine the minimum (the `mcp` library likely needs ≥3.10) and declare it in `pyproject.toml`/`README`. | `<repo>/requirements.txt`; `mcp-servers/openfda/server.py` | IQ-004 reads a declared minimum and PASS/FAILs against it. | Toolkit maintainer | Closed (2026-06-17) — Python 3.12.13 installed via Homebrew and used by the project venv; meets the declared ≥3.10 minimum (enforced by the `server.py` pre-flight). Note the default system `python3` is still 3.9.6, so the server must be launched with the venv interpreter (`.venv/bin/python`).
GIQ-006 | IQ-AI-013 | You cannot ask the running toolkit which version it is. The version (`1.2.0`) lives only in a static file; no running component reports it. In a regulated setting you must be able to confirm at any time that the version in use is the qualified one. | Medium | 21 CFR Part 11 §11.10(k); GAMP 5 change control; ISPE GAMP AI (version management) | Add a version surface — e.g. a `version` tool on the MCP server reading `plugin.json`, or a `VERSION` file surfaced in the catalog. | `mcp-servers/openfda/server.py` or `<repo>/VERSION` | IQ-AI-013 PASS — a runtime query returns the manifest version. | Toolkit maintainer | Closed (2026-06-17) — `server_version()` MCP tool added; returns `plugin.json` version + Python runtime (verified 1.2.0 / 3.12.13).
GOQ-006 | OQ-006 (registration note) | The two sets of hook-setup instructions don't match. The hook's README shows a hard-coded absolute path, while the plugin's `hooks.json` uses a portable `${CLAUDE_PLUGIN_ROOT}` placeholder. A user following the README on a plugin install can register the wrong path and the protection won't fire. | Low | EU Annex 11 cl.4 (clear, correct configuration docs) | Reconcile `hooks/README.md` to explain both paths: plugin installs use the `hooks.json` placeholder automatically; manual/source installs use the absolute path. | `hooks/README.md` | README and `hooks.json` describe one consistent, correct registration per install mode. | Toolkit maintainer | Closed (2026-06-17) — `hooks/README.md` documents all three install modes (plugin / in-repo / manual).
GOQ-007 | OQ-024 (min-config baseline) | There is no single "what you need for this to work" page. The prerequisites (Python version, libraries, MCP registration, hook registration) are scattered. A new user has no one place that states the minimum usable configuration, making a correct install harder to verify. | Low | EU Annex 11 cl.4; GAMP 5 (installation control) | Add a short minimum-configuration document listing every prerequisite and the one command/step to satisfy each. | `docs/minimum-configuration.md` (new) | The document exists and OQ-024's baseline maps to it. | Toolkit maintainer | Closed (2026-06-17) — `docs/minimum-configuration.md` added.
GPQ-004 | PQ-AI-053 | The "is the AI consistent enough?" bar has not been set. The toolkit uses AI to generate evidence, so it must show repeated runs are consistent — but the acceptance threshold for "consistent enough" is a risk-based business decision that has not been made, so the consistency test cannot yet pass or fail. | Low | ISPE GAMP AI (consistency); EU draft Annex 22 | The system owner defines and approves the consistency threshold for the engine's Context of Use; then PQ-AI-053 can be executed. | `Qualification/requirements/URS.md` (URS-AI-053) | Threshold approved; PQ-AI-053 executed against it. | System owner | Open
GPQ-006 | PQ-002, PQ-004, PQ-005, PQ-006, PQ-013 | Some "does it really work end to end" checks still need a live run. Several intended-use behaviours (skills auto-invoking, live eCFR/openFDA fetches, the document builders) can only be fully proven in a live Claude Code session with the dependencies installed and internet access. They are recorded honestly as not-yet-executed — not as passes. | Low (informational) | GAMP 5 (PQ evidence); EU Annex 11 cl.4 | After GIQ-001/002/004 are closed, execute these test-cases in a witnessed live session and record the results. | `Qualification/scripts/` (the named PQ artifacts) | Each listed PQ case executed live with a recorded PASS. | Validation lead | In progress (2026-06-17) — dependencies now installed (`.venv`, 3.12) and the openFDA server is connected, so these are now executable; offline-safe ones (e.g. builders) pass. Remaining live-internet runs (openFDA/eCFR) pending a witnessed session.